## Sample Event Checklist
Event: | Sample Event
Date: | 2025-06-25 | Enter the date in cell B2 in a standard date format, and Excel will fill in all the rest of the dates.
Category | Task | Lead Time | Complete by | Notes
Venue | Reserve Venue(s) | 1 year before | 2024-06-25
Travel | Make hotel reservation | 6 months before | 2024-12-24
Advertise | Create flyer | 6 months before | 2024-12-24
Travel / Honorarium | Send Vendor Setup Form to guest to complete and return | 5.5 months before | 2025-01-08
Travel / Honorarium | Send completed Vendor Setup Form to english.fiscal@osu.edu, as well as the completed Guest Travel Form (filled out by you). The Fiscal Team will use these documents to set up a Spend Authorization & coordinate guest payment. Please also include event flyer or guest invitation. | 5 months before (deadline is 6 weeks before) | 2025-01-21
Coordination | If applicable: Ask bookseller to attend and sell books | 5 months before | 2025-01-21
Coordination | Email guest (hotel reservation #, Video Permission form, access requests, etc.) | 10 weeks before | 2025-04-16
Travel | If applicable, submit Purchase Requisition in Workday with quote sent by hotel. If staying at Blackwell, email SA # to them (or call) | 8 weeks before | 2025-04-30
Travel | Book airplane ticket / rental car. Use CTP (**SA must be approved first) | 8 weeks before | 2025-04-30
Travel | If reimbursing flight (instead of booking through CTP), send english.fiscal@osu.edu the guest's ticketed itinerary, so they can submit an Expense Report on your behalf | 7 weeks before | 2025-05-07
Advertise | Add event to department website via Communications Team Event Form | 6 weeks before | 2025-05-14
Advertise | If applicable, obtain quote for printing flyer by filling out form on UniPrint website. Once obtained, submit Purchase Requisition in Workday to print flyers. Attach quote | 5 weeks before | 2025-05-21
Coordination | If applicable, circulate event sign-up | 5 weeks before | 2025-05-21
Meals | If applicable, ask for attendees' & guest's catering choices | 4 weeks before (deadline is 3 weeks) | 2025-05-28
Meals | If coordinating off-site meal with guest, make reservation and email Fiscal Officer & Faculty Coordinator about borrowing P Card | 4 weeks before | 2025-05-28
Advertise | Advertise on listservs (first) | 4 weeks before | 2025-05-28
Meals | If applicable, get quote from catering contact (if adding gratuity: 18-20%). Send quote with order to English.fiscal@osu.edu. Someone from the Fiscal Team will contact the caterers to pay for the order with a department PCard | 3 weeks before (deadline is 2 weeks) | 2025-06-04
Recording | Deadline to receive Video Permission form; if no permission, cancel filming | 2 weeks before | 2025-06-11
Advertise | Advertise on relevant listservs (second) | 2 weeks before | 2025-06-11
Advertise | Hang flyers in Denney Hall, if applicable | 2 weeks before | 2025-06-11
Coordination | Trip itinerary - send to guest/agency and other relevant parties | 1 week before | 2025-06-18
Advertise | Advertise on relevant listservs (third) | 1 day before | 2025-06-24
Afterwards | Take down flyers | 3 days after | 2025-06-28